## Project Tracker
Create a Project Tracker in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. | Project Tracker
The Start date can be manually input in cell D2, or use the template's sample formula to find the smallest date in the milestone column from the milestone table below. |  | Start date: | 2020-10-05
The End date can be manually input in cell D3, or use the template's sample formula to find the largest date in the milestone column from the milestone table below. |  | End date: | 2021-04-21
Information about the milestone table columns is in cells B4 through G4. | Enter a sequential set of numbers in the column below. | Enter the start date for the milestone or activity in the column below. | Enter the end date for the milestone or activity in the column below | Enter the milestone and/or activity description in the column below. This description will appear in the Project Chart. | Auto calculated. The data below, under this column, is used for charting the milestones and activities. | Auto calculated. Duration of each task
Table headings are in cells B5 through G5. There are two hidden columns: The Start on day and Task Duration columns in cells F5 and G5 are auto calculated and used for creating the Gantt Chart in the Gantt Chart worksheet. Sample data is in cells B6 through E21. The next instruction is in cell A22. | Position | Start Date | End Date | Milestone/Activity | Start on Day | Task Duration
| 1 | 2020-10-05 | 2020-11-05 | Planning and Design | 0 | 32
| 2 | 2020-10-08 | 2020-11-19 | Research | 3 | 43
| 3 | 2020-12-07 | 2021-01-28 | Data Gathering | 63 | 53
| 4 | 2021-01-29 | 2021-02-11 | Data Cleaning | 116 | 14
| 5 | 2020-11-05 | 2021-01-17 | Technique Training | 31 | 74
| 6 | 2020-11-23 | 2020-12-07 | Oral Presentation | 49 | 15
| 7 | 2021-03-07 | 2021-03-14 | Elevator Pitch | 153 | 8
| 8 | 2021-02-12 | 2021-02-23 | Model Training | 130 | 12
| 9 | 2021-02-24 | 2021-03-03 | Review 1
| 10 | 2021-03-04 | 2021-03-18 | Data Cleaning/Gathering 2 | 150 | 15
| 11 | 2021-03-18 | 2021-04-01 | Model Training 2 | 164 | 15
| 12 | 2021-04-01 | 2021-04-08 | Review 2 | 178 | 8
| 13 | 2021-03-24 | 2021-04-21 | Dissertation | 170 | 29
To add more milestones/activities, insert new rows above this line. This is the last instruction in this worksheet. | To add more Milestones/Activities, insert new rows above this line

## Project Chart
Gantt chart with a scrollbar is in this worksheet. Scrollbar starts in cell B29. This is the last instruction in this worksheet.

## About
About this workbook
Enter your data in the Project Tracker worksheet, then scroll through a visual representation of your timeline in the Project Chart worksheet.
The position column in the Project Tracker worksheet, allows you to chart milestones and activities on separate lines. You could, for instance have two milestones/activities that start on the same day and run in parallel. They would overlap in the chart if they had the same position value. Provide two unique values to chart on separate lines. Try it! As the chart concludes, you may notice markers with no text and no duration set at a specific timeline. As the last milestone scrolls off the chart these markers indicate the end of the milestones in the Project Tracker to chart. Simple scroll back or to the beginning to see the chartable milestones.
Guide for screen readers
There are 4 worksheets in this workbook. Project Tracker Project Chart About Dynamic Chart Data (Hidden) The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Dynamic Chart Data Hidden (hidden)
Title of this worksheet is in cell B1. | Dynamic Chart Data
Horizontal scrolling increment heading is in cell B2. To manually increment the data, enter a new value in cell B3. The scrolling page auto updates when the scrollbar is paged forward or backwards in the Gantt Chart worksheet. | horizontal scrolling increment
Auto updated Gantt Chart scrolling value is in cell B3. | 1
Table title is in cell B4. | Dynamic Data Table
Table headings are in cells B5 through E5. A note is in cell F5. This table will chart up to 5 milestones at one time. Do not modify or delete this worksheet or its contents. | milestone | date | Start on Day | duration | <--chart up to 5 milestones at a time
| Research | 2020-10-08 | 3 | 43
| Data Gathering | 2020-12-07 | 63 | 53
| Data Cleaning | 2021-01-29 | 116 | 14
| Technique Training | 2020-11-05 | 31 | 74
| Oral Presentation | 2020-11-23 | 49 | 15